## Sheet1
The Characteristics of Big Data and how they can be used to Quantify its Value
Aston University
| Project Start: | 2018-04-04 |  | =wk 1 |  | Duration in WKs | Predecessors | % Completion | Year | Year 1 | [37 empty] | Year 2
[9 empty] | wk no. | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 37
WBS | TASK | START DATE | ACTUAL START | END DATE | ACTUAL END |  |  |  | w/c | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15
1 | Key Project Milestones
1.01 | IS4001 Assignment Submission | 2018-07-13 | 2018-04-09 | 2018-07-13 | 2018-04-13 | 0 |  | 100% |  | Y
1.02 | Literature Review Substantially Complete | 2018-10-12 |  | 2018-10-12 |  | 0 |  | 0% | [14 empty] | Y
1.03 | Data available for Testing | 2019-04-12 |  | 2019-04-12 |  | 0 |  | 0% | [40 empty] | Y
2 | University Requirements
2.01 | Qualifying Report Production | 2018-12-03 |  | 2019-01-31 |  | 9 |  | 0% | [22 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y
2.02 | Qualifying Report Submission | 2019-01-31 |  | 2019-01-31 |  | 0 |  | 0% | [30 empty] | Y
2.03 | FT-Progression Point | 2019-04-01 |  | 2019-04-05 |  | 1 |  | 0% | [39 empty] | Y
3 | Background Research
3.01 | Background Reading | 2018-04-04 | 2018-04-04 | 2018-07-25 | 2018-05-25 | 16 |  | 90% |  | Y | Y | Y
3.02 | Post IS4001 Literature Review | 2018-07-23 |  | 2018-10-12 |  | 12 | 1.01 | 0% |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
3.03 | Further Literature Reviews | 2018-10-15 | 2018-05-29 | 2019-03-01 | 2018-07-09 | 20 | 3.02 | 0% | [15 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
4 | Dataset Sourcing
4.01 | Consultation with the local SMEs | 2018-04-13 | 2018-04-13 | 2019-04-12 |  | 52 | 1.01 | 5% |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
4.02 | Review SME1 dataset | 2018-08-20 |  | 2018-08-31 |  | 2 | 4.01 | 0% | [7 empty] | Y | Y
4.03 | Feedback to SME1 | 2018-09-03 |  | 2018-09-07 |  | 1 | 4.02 | 0% | [9 empty] | Y
4.04 | Review SME2 dataset | 2018-09-24 |  | 2018-10-05 |  | 2 | 4.01 | 0% | [12 empty] | Y | Y
4.05 | Feedback to SME2 | 2018-10-08 |  | 2018-10-12 |  | 1 | 4.04 | 0% | [14 empty] | Y
4.06 | Review SME3 dataset | 2018-11-12 |  | 2018-11-23 |  | 2 | 4.01 | 0% | [19 empty] | Y | Y
4.07 | Feedback to SME3 | 2018-11-26 |  | 2018-11-30 |  | 1 | 4.06 | 0% | [21 empty] | Y
4.08 | Review SME4 dataset | 2019-01-14 |  | 2019-01-25 |  | 2 | 4.01 | 0% | [28 empty] | Y | Y
4.09 | Feedback to SME4 | 2019-01-28 |  | 2019-02-01 |  | 1 | 4.08 | 0% | [30 empty] | Y
4.1 | Review SME5 dataset | 2019-02-11 |  | 2019-02-22 |  | 2 | 4.01 | 0% | [32 empty] | Y | Y
4.11 | Feedback to SME5 | 2019-02-25 |  | 2019-03-01 |  | 1 | 4.1 | 0% | [34 empty] | Y
4.12 | Review of all data from SMEs | 2019-03-01 |  | 2019-04-12 |  | 6 | 4.11 | 0% | [34 empty] | Y | Y | Y | Y | Y | Y | Y
5 | Model Development
5.01 | Initial framework proposal developed | 2018-10-15 |  | 2019-01-18 |  | 14 | 3.03 | 0% | [15 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
5.02 | Initial testing with sample data | 2018-11-12 |  | 2019-01-18 |  | 10 | 5.01 | 0% | [19 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
5.02 | Quantifying Volume development | 2019-01-21 |  | 2019-06-07 |  | 20 | 5.01 | 0% | [29 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
5.03 | Quantifying Velocity development | 2019-02-25 |  | 2019-07-12 |  | 20 | 5.01 | 0% | [34 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
5.03 | Quantifying Variety development | 2019-04-01 |  | 2019-08-16 |  | 20 | 5.01 | 0% | [39 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
5.04 | Quantifying Veracity development | 2019-05-06 |  | 2019-09-20 |  | 20 | 5.01 | 0% | [44 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
5.04 | Synthesis of quantifying characteristics | 2019-06-10 |  | 2019-10-25 |  | 20 | 5.04 | 0% | [49 empty] | Y | Y | Y | Y | Y
5.05 | Verification testing with sample data | 2019-04-15 |  | 2019-12-20 |  | 36 | 5.02 | 0% | [41 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
6 | Leave, Uni Closed Days & BHs
6.1 | Leave, Uni Closed Days & BHs |  |  |  |  | 7 |  |  |  |  | Y | [7 empty] | Y | Y | [12 empty] | Y | Y | [9 empty] | Y | [6 empty] | Y
Note on C5: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E5: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.

## Sheet2
1 | -3
2 | 0
3 | 0
4 | 0
5 | 0
6 | -1
7 | -2
2018-04-01